## タスク
プロジェクト名 |  | 不動産システム | [5 empty] | 開始日
終了日
No. | 作業名 |  | 担当者 | 期間(予定) |  | 期間(実績) |  |  | ステータス | 1 | [30 empty] | 2 | [27 empty] | 3 | [30 empty] | 4 | [29 empty] | 5 | [30 empty] | 7 | [30 empty] | 8 | [30 empty] | 9 | [29 empty] | 10 | [30 empty] | 11 | [29 empty] | 12
|  |  |  | 開始日 | 終了日 | 開始日 | 終了日 |  |  | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[8 empty] | 進捗率 |  | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1 | 環境構築 |  | 朝・趙 | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2023-04-18 | 100% | 完了 | bar: 火
2 | 機能一覧作成 |  | 朝・趙 | 2023-04-18 | 2023-04-19 | 2023-04-19 | 2023-04-19 | 100% | 完了 | bar: 火 to 水
3 | 画面遷移図作成 |  | 朝・趙 | 2023-04-18 | 2023-04-19 | 2023-04-19 | 2023-04-19 | 100% | 完了 | bar: 火 to 水
4 | レイアウト作成 |  | 朝・趙 | 2023-04-18 | 2023-04-19 | 2023-04-19 | 2023-04-19 | 100% | 完了 | bar: 火 to 水
5 | ER図作成 |  | 朝・趙 | 2023-04-18 | 2023-04-19 | 2023-04-19 | 2023-04-19 | 50% | 作成中 | bar: 火 to 水
6 | 製造 |  | 朝・趙 | 2023-04-20 | 2023-04-25 | bar: 木 to 土; 月 to 火
| UTケース作成・実施 |  | 朝・趙 | 2023-04-26 | 2023-04-27 | bar: 水 to 木
| ITケース作成・実施 |  | 朝・趙 | 2023-04-27 | 2023-04-28 | bar: 木 to 金
| 発表 |  | 朝・趙 | 2023-04-29 | 2023-04-29 | bar: 土

## 2023年の祝日
■参考）2023年の祝日
（内閣府）「国民の祝日」について
https://www8.cao.go.jp/chosei/shukujitsu/gaiyou.html
令和5年（2023年）の国民の祝日
|  | 名称 | 日付 | 備考
|  | 元日 | 2022-01-01
|  | 休日 | 2022-01-02 | 祝日法第3条第2項による休日
|  | 成人の日 | 2022-01-09
|  | 建国記念の日 | 2022-02-11
|  | 天皇誕生日 | 2022-02-23
|  | 春分の日 | 2022-03-21
|  | 昭和の日 | 2022-04-29
|  | 憲法記念日 | 2022-05-03
|  | みどりの日 | 2022-05-04
|  | こどもの日 | 2022-05-05
|  | 海の日 | 2022-07-17
|  | 山の日 | 2022-08-11
|  | 敬老の日 | 2022-09-18
|  | 秋分の日 | 2022-09-23
|  | スポーツの日 | 2022-10-09
|  | 文化の日 | 2022-11-03
|  | 勤労感謝の日 | 2022-11-23

## 機能一覧
機能一覧
大分類 | 中分類 | 小分類
物件情報管理 | 物件 | 新規登録
編集
削除
検索
| 部屋 | 新規登録
編集
削除
一覧
物件一覧
部屋一覧
賃貸管理 | 賃貸一覧
賃貸ステータス更新
ユーザー管理 | 新規登録
編集
削除

## 画面遷移図
新規ok
登録画面に戻る
新規ok
登録画面に戻る
物件登録画面に
戻るボタンから一覧画面まで
ここに表示
部屋の情報
情報を削除
最新情報

## レイアウト
登録画面 | 新規登録画面 | 物件一覧
更新もこの画面
に
情報登録画面 | 部屋詳細